# Implementation Roadmap & Delivery Plan

Fleet & Transport Management Platform — Discovery to Production

Approach: business-first, billing-first, then technology and implementation.

# 1. Delivery Strategy

The project should be delivered in controlled phases. The first release is intentionally focused on the owner's real pain: replacing paper/Excel month-end billing and centralizing the operational data needed to produce correct bills.

| Stage | Primary outcome | Gate to proceed |
| --- | --- | --- |
| 0. Discovery | Approved business rules and source-of-truth definitions. | Owner signs off billing rules and master-data model. |
| 1. Foundations | Vehicles, drivers, firms, contracts, routes, documents. | Masters are validated against live business data. |
| 2. Daily Operations | Daily trip/assignment entry and editing. | A full month can be recorded without paper duplication. |
| 3. Billing Engine | Automated bill calculation, preview and PDF. | Reference Excel bills reproduce correctly. |
| 4. Expenses & Payments | Fuel/toll/maintenance/loading costs and factory payment tracking. | Monthly financial view reconciles to current records. |
| 5. Dashboard & Reports | Owner-level visibility by month, firm and vehicle. | Owner can answer core monthly questions without Excel. |
| 6. Pilot & Rollout | Production use with controlled historical/current data. | Pilot month reconciled and approved. |

# 2. Phase 0 — Business Discovery

Collect the commercial contracts/rate sheets for the 3–4 firms.

Build the full capacity → average table.

Confirm the complete KM → rounds/hiring slab table, including short-trip rules and >700 km behavior.

Confirm the base hiring rate dimension (vehicle/capacity/route/firm/contract).

Confirm HSD rate source and effective-date handling.

Confirm toll source and billability.

Confirm the exact factory bill layout and bill numbering sequence.

Collect 2–3 additional representative bills for different vehicles/route patterns.

## Phase 0 deliverables

Approved BRD

Approved billing rules specification

Initial master-data template

Reference bills for automated calculation testing

# 3. Phase 1 — Master Data & Foundations

Vehicle master with capacity, type and billing profile.

Driver master and daily wage rate.

Firm/customer master.

Routes and pickup/drop locations.

Contract and rate-version structure.

Vehicle documents and expiry metadata.

Basic user authentication and owner account.

## Definition of done

All 50 vehicles can be loaded and searched.

Every active vehicle has a valid capacity/billing profile.

All firms and current drivers are represented.

The owner can inspect the commercial configuration without developer intervention.

# 4. Phase 2 — Daily Operations

Daily operation screen with fast vehicle/date/firm/route/driver selection.

KM capture and automatic rounds calculation.

Trip history, search and correction.

Monthly operational summary.

Optional limited operations-employee role if the owner decides to stop paper registers.

## Definition of done

One daily operation can be recorded in seconds rather than reconstructed at month end.

The system can reproduce the trip list used by the reference bill.

# 5. Phase 3 — Billing Engine

HSD litres calculation.

HSD amount calculation.

Hiring rounds and base rate calculation.

Toll inclusion.

Trip total and monthly aggregation.

Firm/month bill preview.

Finalization workflow.

PDF bill generation.

Historical rule-version storage.

## Definition of done

Reference bills match the system calculation to the agreed rounding policy.

Owner can generate a final PDF without using Excel for calculation.

Historical finalized bills remain reproducible after rate changes.

# 6. Phase 4 — Expenses & Payments

Fuel expense ledger and receipt attachments.

Toll expense import/manual entry.

Maintenance/repair expense ledger.

Polypack loading/unloading contractor charges.

Other expense categories.

Factory payment entry and bill status.

Outstanding amount per firm and bill.

## Definition of done

Owner can see factory revenue and actual company expenses separately.

Monthly outstanding balances can be reviewed without opening multiple spreadsheets.

# 7. Phase 5 — Dashboard & Reports

Monthly business dashboard.

Vehicle-wise revenue/expense/contribution.

Firm-wise billing and payment.

Fuel/toll/maintenance summaries.

Driver wage summary.

Document expiry alerts.

## Definition of done

The owner can answer: how much was billed, how much was received, what was spent, which vehicles generated revenue, and what needs attention — from one dashboard.

# 8. Phase 6 — Pilot, Reconciliation and Rollout

1. Select one billing month as a controlled pilot.

2. Enter/reference the same trips used in the paper/Excel process.

3. Generate bills in parallel with the current Excel process.

4. Compare line-by-line: KM, average, HSD litres, HSD amount, rounds, hiring, toll and total.

5. Resolve any difference and lock the calculation rules.

6. Run one full month with the new system as the primary source.

7. Archive the old Excel as reference rather than as the operating system.

# 9. Testing Strategy

| Test level | What to verify | Examples |
| --- | --- | --- |
| Unit calculation tests | Every billing formula in isolation. | KM/AVG; HSD×rate; rounds×base hiring; trip total. |
| Rule boundary tests | KM at and around each slab boundary. | 499, 500, 501, 699, 700, 701 and short-trip boundary values. |
| Vehicle profile tests | Different capacities/rates. | 12,000; 23,000; 29,000; 34,000 capacity examples from workbook. |
| Regression tests | Historical bills remain unchanged. | Re-run approved June reference bills after rate configuration changes. |
| User acceptance | Owner verifies real workflows. | Add trip, review month, generate bill, record payment. |
| PDF tests | Printed/generated output is correct. | Bill numbering, totals, dates, vehicle and customer details. |

# 10. Data & Document Preparation Checklist

| Data set | Required fields | Source |
| --- | --- | --- |
| Vehicles | Registration, type, capacity, active status, billing profile. | Current vehicle list / Excel. |
| Drivers | Name, daily wage, active status, contact if needed. | Current driver list. |
| Firms | Legal/billing name, address/GST details if applicable. | Contracts/bills. |
| Contracts | Start/end, rate version, average mapping, hiring slabs, toll rules. | Signed agreements/rate sheets. |
| Routes | Pickup, drop, route code/distance if fixed. | Current operations records. |
| Documents | Type, issue/expiry date, file path/attachment. | Physical files. |
| Reference bills | Bill number, month, vehicle, line-level inputs and totals. | Current Excel bills. |

# 11. Recommended Future Enhancements (after stable V1)

FASTag statement import.

Fuel receipt image/OCR extraction.

WhatsApp-assisted receipt capture.

Operations employee mobile/web data-entry screen.

Driver app only if the business later wants direct driver updates.

GPS integration.

Tally/accounting integration.

Advanced profitability and analytics.

# 12. Project Risks and Controls

| Risk | Impact | Control |
| --- | --- | --- |
| Wrong billing rule interpretation | High | Use signed contract/rate sheets and reference bills before coding final formulas. |
| Rate changes after rollout | High | Versioned effective-dated billing configuration. |
| Incomplete daily records | High | Validation, missing-data alerts and optional operations data-entry role. |
| Mismatch between paper/Excel and system | High | Parallel pilot month and line-level reconciliation. |
| Overbuilding | Medium | Keep driver app/GPS/OCR out of V1. |
| Historical data quality | Medium | Start with current/pilot month; migrate older data only where useful. |

# 13. Final Deliverables by the End of Business Design

Approved Business Requirements Document.

Approved Billing Rules & Calculation Specification.

Requirements tracker and open-question log.

Reference billing datasets for automated tests.

Master-data templates.

Initial screen/workflow map.

Confirmed MVP scope.

Then — database design, API contracts and technology selection.